## Sheet1
XHAW5112 TIMESHEET / ACTIVITY LOG
# | DATE | DAY | TIME IN | TIME OUT | TOTAL HOURS | ACTIVITY TYPE | DESCRIPTION OF WORK DONE | GROUP COLLABORATION (Y/N) | COLLABORATED WITH (NAMES) | NOTES / CHALLENGES | GIT COMMIT MADE (Y/N) | GIT COMMIT LINK MESSAGE
1 | 2025-07-31 | Thursday | nan | nan | nan | Planning | All proposals finished | Y | Daniel, Mukhesi, Lonwabo | All proprosals completed and submitted | N
2 | 2025-08-01 | Friday | nan | nan | nan | Planning | Website and Mobile app proposals chosen | Y | Daniel, Mukhesi, Lonwabo | None | N
3 | 2025-08-01 | Friday | nan | nan | nan | Planning | Updated group proposal document | Y | Daniel, Mukhesi, Lonwabo | None | N
4 | 2025-08-11 | Monday | 15:00 | 17:30 | 2h 30m | Development | Mobile app created & homepage content added | N | Daniel | None | N
5 | 2025-08-12 | Tuesday | 12:00 | 20:00 | 6h 30m | Development | Website is created and all screens are added | N | Lonwabo | None | N
6 | 2025-08-12 | Tuesday | nan | nan | nan | Meetings | Online meeting | Y | Daniel, Mukhesi, Lonwabo | Meeting to discuss the current chosen Website and mobile app proposal and their designs | N
7 | 2025-08-13 | Monday | 12:00 | 20:00 | 6h 30m | Development | Adding content into website and app | Y | Daniel, Mukhesi, Lonwabo | Agreeing on what is neccesary to add to website and app | N
8 | 2025-08-13 | Wednesday | 15:00 | 20:00 | 5h | Design | Updated website & mobile app UI design in figma | Y | Daniel, Mukhesi, Lonwabo | Updated the website and mobile app to include better ui layout and content | N
9 | 2025-08-14 | Thursday | 15:00 | 17:00 | 2h | Design | Finished website & mobile app UI design | Y | Daniel, Mukhesi, Lonwabo | Updated the website and mobile app to include better ui layout, content and pictures | N
10 | 2025-08-14 | Thursday | 10:00 | 10:10 | 10m | Meetings | Interface and Flow meeting with sir | Y | Daniel, Mukhesi, Lonwabo | Discussed our currently chosen proposal with sir and the improvement we can make to it. | N
11 | 2025-08-28 | Thursday | 16:00 | 20:00 | 4h | Development | Improved in-app UI design & added mobile app course types page content | Y | Daniel, Mukhesi | None | N
12 | 2025-08-28 | Thursday | unsure | unsure | nan | Meetings | Progress update with sir | Y | Daniel, Mukhesi | Presented currently finished app and website UI design proposal | N
13 | 2025-08-31 | Sunday | 17:00 | 20:00 | 3h | Development | Improved in-app UI design & added mobile app six week/month courses page content | Y | Daniel, Mukhesi | Slight issue with header spacing solved | N
14 | 2025-09-02 | Tuesday | 14:00 | 23:45 | 9h 45m | Development | 2025 Created mobile app dropdown menu, added mobile app site navigation & added content to about us page | N | Daniel | I struggled a lot implementing the dropdown menu. I settled on using a Modal popup that would appear and dissapear when pressing the burger button. | N
15 | 2025-09-02 | Tuesday | 14:00 | 18:00 | 6h | Development | Added Course calculations to website | N | Daniel | instead of transferrring data from pages together, rather have the calculations and data on one screen | N
16 | 2025-09-04 | Thursday | 10:00 | 20:00 | 10h | Development | Improved mobile app dropdown menu & page navigation | N | Daniel | Improved dropdown menu layout, animation and site navigation buttons. Added screen darken overlay when opening dropdown menu, rendering on wrong layer | N
17 | 2025-09-10 | Wednesday | 16:00 | 20:00 | 2h | Testing | Testing of website (Calculations, experience, accessibilty and interest) | Y | Daniel, Mukhesi | None | N
18 | 2025-09-10 | Wednesday | unsure | Unsure | nan | Meetings | Online meeting | Y | Daniel, Mukhesi, Lonwabo | None | N
19 | 2025-09-11 | Thursday | Unsure | Unsure | nan | Meetings | Meeting with sir | Y | Daniel, Mukhesi, Lonwabo | Discussed adding a Modern font for website. Clickable images/lightbox. Footer, search icon. App function polishing. | N
20 | 2025-09-12 | Friday | 12:00 | 16:00 | 4h | Development | Courses types page navigation function added | Y | Daniel, Mukhesi | None | N
21 | 2025-09-14 | Sunday | 14:00 | 23:00 | 9H | Development | Six week/month pages now takes in and saves chosen courses to array | N | Daniel | Struggled with accessing the array during runtime, fixed by declaring it outside of App() function with let | N
22 | 2025-09-15 | Monday | 15:00 | 21:00 | 6h | Development | Added currently chosen courses functionality to bookings page & added modal confirmation popup too course pages | N | Daniel | None | N
23 | 2025-09-16 | Tuesday | 15:00 | 19:00 | 4h | Development | Added the ability to remove a chosen course on bookings page | Y | Daniel, Mukhesi | Updating the pages info after removing a course was somewhat of an issue. However it was solved by using a modal popup to force reload the page thus updating the information during app runtime | N
24 | 2025-09-17 | Wednesday | 8:00 | 22:00 | 10h | Development | Added search feature and lighboxes to images inside website | N | Lonwabo | Adding search terms for results, creating sound logic that will not affect the website and not ruin the flow and design of the website | N
25 | 2025-09-17 | Wednesday | unsure | unsure | nan | Meetings | Online meeting | Y | Daniel, Mukhesi, Lonwabo | None | N
26 | 2025-09-17 | Wednesday | unsure | unsure | nan | Meetings | Progress update with sir | Y | Daniel, Lonwabo | Discussed Website - alignment of button and images. Slogan in banner section. Lightbox to be polished. App polishing to finalised (addresses, icons, images, socials, calculations, burger menu update). Dry-run, Thursday, 9 October 2025. | N
27 | 2025-09-19 | Friday | 17:00 | 21:30 | 4h 30m | Development | Added currently selected courses & their individual prices to cart page on mobile app | N | Daniel | None | N
28 | 2025-09-20 | Saturday | 15:00 | 22:00 | 7h | Development | Fixed mobile app dropdown menu overlay render layer bug & added calculate fees functionality too mobile app cart screen | N | Daniel | None | N
29 | 2025-09-21 | Sunday | 15:00 | 23:00 | 8h | Development | Improved overall mobile app UI, added images to mobile app contact us page & Social media button functionality | Y | Daniel, Mukhesi | None | N
30 | 2025-10-08 | Wednesday | 15:00 | 20:00 | 5h | Planning | Powerpoint presentation created & Presentation dryrun preporations finished | Y | Daniel, Mukhesi, Lonwabo | First version of powerpoint created for dryrun | N
31 | 2025-10-10 | Friday | 18:00 | 20:00 | 2h | Planning | Improved powerpoint presentation astetics | N | Daniel | Improved color scheme, added pictures and slide transitions | N
32 | 2025-10-15 | Wednesday | 15:00 | 16:00 | 1h | Planning | Improved powerpoint presentation astetics and content | N | Daniel | Removed redundant slides and finished adding graphics to slides | N